## Instructions
Instructions
This is a very simple one page project report that should work for most small projects.
It is based on the recommended practice in the PMI and APM Bodies of knowledge.
Colour coding
Headings | Set up at the start of the project | Data Entry | Calculated Field do not edit
Project Title | Text Description of your project
Report Date | Status date of the report, this is the date the data was valid, normaly the end of the month.
Schedule | Status | Planned Date | Forecast / Actual Date |  |  | Owner | Traffic Light | Comment
Training Ready | Complete | 2025-01-11 | 2025-01-01 |  |  | Training | -10
Go Live | Complete | 2025-01-12 | 2025-01-20 |  |  | Operations | 8
Milestone | On-going | Target Date | Actual date if complete or forecast date if on-going |  |  | Accountable Person | Traffic light calculated using the tolerances in the validation sheet
Cost Account | Budget | Planned Cost to Date | Actual Cost to Date | Estimate to Complete | Forecast Cost at Completion | Owner | Traffic Light | Comment
Design | 1000 | 500 | 500 | 200 | 700 | IT | 70%
Coding | 1600 | 600 | 500 | 1000 | 1500 | IT | 93.75%
Testing | 500 | 400 | 420 | 200 | 620 | IT | 124%
Training | 300 | 300 | 100 | 200 | 300 | IT | 100%
Licences | 200 | 100 | 120 | 85 | 205 | IT | 102.5%
Cost Heading | Budget | Expected cost to date | How much has been spent | How much to spend to complete | Sum of AC+ETC | Who is accountable for this budget | Calculated traffic light tolerances in the validation sheet
Total | 3600 | 1900 | 1640 | 1685 | 3325 |  | 92.36%
Other Measure | Comment
Resources | Comments go here | [6 empty] | 1 | Set to <1 for green, 1 for yellow and >1 for red
Quality | [7 empty] | 0.8
Progress since last report
Activities planned for next period
Risk | Status | Probability | Impact | Priority Score | Risk Reduction Action |  | Owner | Comment
Technology might fail | Open | Med | VHi | 0.4 | Pilot first |  | IT
Resources become unavailable | Open | Lo | Lo | 0.03 | Contractors |  | IT
Delay in parts deliver | Open | Lo | High | 0.12 | Pre-order |  | IT
Bugs in Software | Open | VLo | VHi | 0.08 | Test |  | IT
Poor User Feedback | Open | VLo | VLo | 0.005 | Early User Input |  | IT
Risk Description | Status filed set in validation sheet | Classic five point scale and weighting from PMI and APM Bodies of Knowledge. |  |  | Risk Reduction Action |  | Owner of risk
Issues | Status | Impact | Owner | Issue Management Action
Technology incompatibile | New | High | IT | Look for alternative technology
Description | Status from validation sheet follow APM process | Impact on project overall |  | Agreed/ proposed action

## Valudations Settings
Settings
Milestone Status
Complete
On-going
Milestone Tolerance
Late | 5
Early | -5
Cost Tolerance
Underspend | 90%
Overspend | 110%
Quantitative Indicators
Green | Less than 1
Yellow | 1
Red | Greater than 1
Risk
Risk Status
Open | Risk live
Closed | Risk can longer happen most likely because it is in the past
Risk Probability and Impact Scale
| Probability Scale | Impact Scale | Risk Colours
VLo | 0.1 | 0.05 | Red | 0.24
Lo | 0.3 | 0.1 | Yellow | 0.06
Med | 0.5 | 0.2 | Green | 0
High | 0.7 | 0.4
VHi | 0.9 | 0.8
For scoring scheme visit https://www.praxisframework.org/en/library/probability-impact-assessment
Issue Management
Status | Impact
New | Low
Evaluated | Medium
Resolved | High
Change Management
Status
New
Evaluated
Proposed
Approved
Rejected
Defered

## Report Sheet
Project Title |  |  |  |  | Report Date
Summary Report
Schedule | Status | Planned Date | Forecast / Actual Date |  |  | Owner | Traffic Light | Comment
IT Live | Complete | 2025-01-10 | 2025-01-10 |  |  | IT | 0
Training Ready | Complete | 2025-01-11 | 2025-01-01 |  |  | Training | -10
Go Live | Complete | 2025-01-12 | 2025-01-20 |  |  | Ops | 8
Review | Complete | 2025-01-12 | 2025-01-20 |  |  | Ops | 8
Cost Account | Budget | Planned Cost to Date | Actual Cost to Date | Estimate to Complete | Forecast Cost at Completion | Owner | Traffic Light | Comment
Design | 1000 | 500 | 500 | 200 | 700 | IT | 70%
Coding | 1600 | 600 | 500 | 1000 | 1500 | IT | 93.75%
Testing | 500 | 400 | 420 | 200 | 620 | IT | 124%
Training | 300 | 300 | 100 | 200 | 300 | IT | 100%
Licences | 200 | 100 | 120 | 85 | 205 | IT | 102.5%
Total | 3600 | 1900 | 1640 | 1685 | 3325 |  | 92.36%
Other Measure | Comment
Resources | [7 empty] | 1
Quality | [7 empty] | 0.8
Progress since last report
Activities planned for next period
Risk | Status | Probability | Impact | Priority Score | Risk Reduction Action |  | Owner | Comment
Technology might fail | Open | Med | VHi | 0.4 | Pilot first |  | IT
Resources become unavailable | Open | Lo | Lo | 0.03 | Contractors |  | IT
Delay in parts deliver | Open | Lo | High | 0.12 | Pre-order |  | IT
Bugs in Software | Open | VLo | VHi | 0.08 | Test |  | IT
Poor User Feedback | Open | VLo | VLo | 0.005 | Early User Input |  | IT
Issues | Status | Impact | Owner | Issue Management Action
Technology incompatibile | New | High | IT | Look for alternative technology
Changes | Status | Impact on Time | Inpact on Cost | Owner |  |  | Traffic Light | Comment
1
1
1
1
Template Provided by Parallel Project Training |  | https://www.parallelprojecttraining.com/